VERIDIAN BANK

SentinelAI Fraud Detection Platform

WEEKLY STATUS REPORT

SentinelAI Fraud Detection Platform

Template & Sample Reporting Periods

| Prepared By: | Mautik Patel, Project Delivery Manager |
| --- | --- |
| Distribution: | Sponsor, Steering Committee, Workstream Leads |
| Cadence: | Weekly, every Friday COB |

# Overall Project Health Summary

| Dimension | RAG | Commentary |
| --- | --- | --- |
| Schedule | Amber | Model risk validation start delayed 2 weeks pending vendor contract; mitigation in progress (R-03) |
| Budget | Green | Tracking at 98% of planned spend through end of Phase 4 |
| Scope | Green | No unapproved scope changes; one change request (mobile alerts) deferred to Phase 2 backlog |
| Resources | Amber | Fraud Ops analyst availability for pilot labeling below plan; backfill contractor request submitted |
| Risk | Amber | Two high risks open (R-01 data quality, R-02 latency); mitigation plans active |

## Status Report – Week 18 (May 4 – May 8, 2026)

| Dimension | RAG | Commentary |
| --- | --- | --- |

- Completed feature engineering for velocity-based features; validated against holdout dataset

- Signed vendor contract with external model risk validator (resolves scheduling risk R-03 partially)

- Delivered RAID log update to Steering Committee; two risks downgraded from High to Medium

- Begin champion/challenger test harness configuration

- Complete UAT test case authoring with QA and Fraud Ops

- Kick off fairness testing dataset preparation (FR-14)

- R-01 (data quality): re-labeling sample now 60% complete, on track for May 22 completion

- R-02 (latency): switch vendor POC test scheduled for May 15

## Status Report – Week 19 (May 11 – May 15, 2026)

| Dimension | RAG | Commentary |
| --- | --- | --- |

- Switch vendor POC latency test completed: P95 = 178ms, within target (closes R-02 to Low)

- UAT test case set finalized (32 cases across 4 functional areas)

- Fairness testing dataset prepared; initial disparity analysis shows 6% gap, within threshold

- Begin formal UAT execution with Fraud Ops analysts (2-week window)

- Finalize case management API rate-limit increase with vendor (I-02)

- Prepare go-live readiness checklist draft for Steering Committee review

- R-01 (data quality): on track, re-labeling 85% complete

- I-02 (API rate limits): vendor committed to Jun 2026 increase; interim queueing buffer holding steady