VERIDIAN BANK

SentinelAI Fraud Detection Platform

PROJECT CHARTER

SentinelAI Fraud Detection Platform

Real-Time, ML-Driven Card Fraud Detection & Decisioning

| Document Owner: | Mautik Patel, Project Delivery Manager |
| --- | --- |
| Sponsor: | Sarah Whitfield, Chief Risk Officer |
| Version: | 1.0 (Approved) |
| Date: | January 12, 2026 |
| Classification: | Confidential – Internal Use Only |

# 1. Project Purpose & Justification

Veridian Bank's card fraud losses have grown 42% over the past 24 months, driven primarily by card-not-present (CNP) e-commerce fraud and account takeover schemes. The current fraud detection engine relies on static, rules-based logic that was last materially updated in 2021. This has produced two compounding problems: fraud losses of approximately $18.4M in the trailing twelve months, and a false-positive rate of 6.8% that generates over 40,000 unnecessary transaction declines per month, directly harming customer experience and contributing to a measurable increase in card attrition.

SentinelAI will replace the legacy rules engine with a real-time, machine-learning-based fraud scoring platform. The project is sponsored by the Office of the Chief Risk Officer and is one of three initiatives designated as a 2026 enterprise priority under the Bank's Risk Modernization Program.

# 2. Business Objectives & Success Criteria

| Objective | Success Criteria | Target Date |
| --- | --- | --- |
| Reduce fraud losses | Reduce annualized fraud losses by ≥35% vs. FY2025 baseline | Q4 2026 |
| Reduce false positives | Cut false-positive decline rate from 6.8% to ≤4.0% | Q4 2026 |
| Real-time performance | Achieve ≤200ms P95 transaction scoring latency | Go-live |
| Analyst productivity | Reduce manual case review volume by 30% | Q1 2027 (90 days post go-live) |
| Regulatory alignment | Pass independent model risk validation (SR 11-7 aligned) | Prior to go-live |

# 3. Scope

## 3.1 In Scope

- Real-time ML fraud scoring engine for credit and debit card transactions (POS and CNP)

- Feature engineering pipeline using Snowflake as the analytical data layer

- Model development, validation, and champion/challenger testing framework

- Case management workflow integration for the Fraud Operations team

- Integration with the existing card authorization switch (real-time API)

- Explainability layer (reason codes) for analyst review and regulatory response

- Model monitoring, drift detection, and retraining pipeline

## 3.2 Out of Scope

- Wire transfer and ACH fraud detection (separate initiative, Treasury Fraud Program)

- Merchant-side fraud/chargeback dispute automation

- Replacement of the core card issuance or authorization switch platform

- New customer-facing fraud alert mobile app (Phase 2 candidate)

# 4. Key Stakeholders

| Name / Role | Organization | Interest / Influence |
| --- | --- | --- |
| Sarah Whitfield, CRO | Risk Management | Executive Sponsor; accountable for fraud loss KPIs |
| Mautik Patel | PMO / BI Delivery | Project Delivery Manager; owns plan, budget, and delivery |
| David Okonjo, Head of Fraud Ops | Fraud Operations | Primary business owner of case workflow and analyst tooling |
| Priya Nataraj, Head of Data Science | Data & Analytics | Owns model design, training, and validation |
| Marcus Webb, Head of Card Payments | Card Payments | Owns authorization switch integration and uptime SLAs |
| Legal & Compliance | Compliance | Regulatory sign-off; model risk governance (SR 11-7) |
| Enterprise IT Infrastructure | IT | Provides compute, network, and production environment support |

# 5. High-Level Milestones

| Milestone | Target | Owner |
| --- | --- | --- |
| Charter approval & funding release | Jan 2026 | CRO / Sponsor |
| Requirements sign-off (BRD/FRD) | Feb 2026 | Mautik Patel |
| Data pipeline & feature store live (dev) | Apr 2026 | Data Engineering |
| Model v1 trained & validated | Jun 2026 | Data Science |
| Champion/challenger pilot (10% traffic) | Jul 2026 | Fraud Ops / Data Science |
| Model risk validation sign-off | Aug 2026 | Compliance |
| Full production go-live | Sep 2026 | Mautik Patel |
| Post-implementation review | Dec 2026 | Mautik Patel |

# 6. Budget Summary

| Category | Amount (USD) | % of Total |
| --- | --- | --- |
| Data science & model development (staff) | $820,000 | 34% |
| Engineering & integration (staff) | $610,000 | 25% |
| Cloud/Snowflake compute & storage | $340,000 | 14% |
| Third-party fraud data & model tooling licenses | $280,000 | 12% |
| Model risk validation (external) | $150,000 | 6% |
| Contingency (9%) | $200,000 | 9% |
| Total | $2,400,000 | 100% |

# 7. Assumptions & Constraints

## 7.1 Assumptions

- Historical transaction data (24+ months) is available and of sufficient quality in the existing data warehouse

- Fraud Operations will allocate two senior analysts to the pilot for labeling and feedback

- The card authorization switch vendor can support a new real-time scoring API call within existing latency budgets

## 7.2 Constraints

- Go-live must occur before the November – January peak fraud season

- Model must be explainable to satisfy Reg E dispute-response and fair-lending requirements

- No downtime permitted on the production card authorization path during cutover

# 8. Approval

| Name / Role | Signature | Date |
| --- | --- | --- |
| Sarah Whitfield – Chief Risk Officer (Sponsor) |  | Jan 12, 2026 |
| Mautik Patel – Project Delivery Manager |  | Jan 12, 2026 |
| David Okonjo – Head of Fraud Operations |  | Jan 12, 2026 |