PURNIMA BANK

SentinelAI Fraud Detection Platform

RAID LOG & RISK REGISTER

SentinelAI Fraud Detection Platform

Risks, Assumptions, Issues & Dependencies

| Document Owner: | Mautik Patel, Project Delivery Manager |
| --- | --- |
| Version: | Live document – v1.4 |
| Last Updated: | May 15, 2026 |
| Review Cadence: | Weekly (core team) / Monthly (Steering Committee) |

# 1. Risk Scoring Methodology

Risk score = Probability (1–5) × Impact (1–5). Scores 12–25 = High (red), 6–11 = Medium (amber), 1–5 = Low (green). High risks are escalated to the Steering Committee within 48 hours of identification.

# 2. Risk Register

| ID | Risk Description | Category | Prob (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | Historical fraud labels are inconsistently tagged pre-2024, degrading model training quality | Data | 4 | 4 | 16 | Run a data quality audit sprint; engage Fraud Ops to re-label a stratified sample of 5,000 historical cases | Priya N. | Open |
| R-02 | Card authorization switch vendor cannot meet 200ms latency SLA for the new scoring hook | Technical | 3 | 5 | 15 | Early proof-of-concept load test in Feb 2026; fallback fail-open design already in FRD (FR-04) | Marcus W. | Open |
| R-03 | External model risk validator has a 10-week backlog, threatening the Aug 2026 sign-off date | Schedule | 3 | 4 | 12 | Engaged validator in parallel from Feb 2026 rather than waiting for model completion; weekly check-ins | Mautik P. | Mitigating |
| R-04 | Model exhibits disparate false-positive impact across zip-code income tiers during fairness testing | Regulatory | 2 | 5 | 10 | Fairness testing built into FR-14; Legal engaged early to define acceptable disparity thresholds | Compliance | Open |
| R-05 | Fraud Operations analysts under-resourced for pilot labeling, slowing champion/challenger feedback | Resource | 3 | 3 | 9 | Secured 2.0 FTE commitment from Fraud Ops leadership in the Project Plan; contingency to backfill with contractors | David O. | Mitigating |
| R-06 | Snowflake compute costs exceed budget during historical backfill due to inefficient queries | Financial | 2 | 3 | 6 | Cost monitoring dashboards and query optimization review before full backfill run | Data Eng. | Closed |
| R-07 | Key data scientist departs mid-project, causing knowledge loss on feature engineering | Resource | 2 | 3 | 6 | Documentation-first culture enforced; pair programming on critical pipeline components | Priya N. | Open |
| R-08 | Peak holiday transaction volume (Nov–Jan) exceeds load-tested throughput | Technical | 2 | 4 | 8 | Load testing at 1.5x projected peak volume scheduled for August 2026 | Eng. Team | Open |

# 3. Assumptions

| ID | Assumption | Validation Method | Status |
| --- | --- | --- | --- |
| A-01 | 24+ months of labeled transaction history exists and is accessible in the warehouse | Data profiling in Phase 2 | Validated |
| A-02 | Card authorization switch supports a synchronous API callout without re-architecture | Vendor technical workshop | Validated |
| A-03 | Fraud Ops leadership can commit 2.0 FTE analysts for pilot period without backfilling BAU | Resource confirmation from Head of Fraud Ops | Validated |

# 4. Issues

| ID | Issue | Raised | Severity | Resolution / Status |
| --- | --- | --- | --- | --- |
| I-01 | Digital channel device-fingerprint data has 22% missing values for transactions pre-2025 | Mar 2026 | Medium | Feature engineered with missingness indicator; revalidate model impact |
| I-02 | Case management system API rate limits cap auto-case creation at 500/min | Apr 2026 | Medium | Vendor increasing limit to 1,500/min by Jun 2026; interim queueing buffer implemented |

# 5. Dependencies

| ID | Dependency | Depends On | Target Date |
| --- | --- | --- | --- |
| D-01 | Scoring API integration cannot begin until switch vendor confirms hook availability | Card Payments / Vendor | Apr 2026 |
| D-02 | Go-live cannot proceed without independent model risk validation sign-off | External Validator / Compliance | Aug 2026 |