## OverView
PURNIMA BANK
SentinelAI Fraud Detection Platform
RACI MATRIX
SentinelAI Fraud Detection Platform
Roles & Responsibilities Across the Project Lifecycle
Document Owner: | Mautik Patel, Project Delivery Manager
Version: | 1
Date: | 2026-01-20
Legend: | R = Responsible, A = Accountable, C = Consulted, I = Informed

## Sheet2
Activity | Sponsor (CRO) | Delivery Mgr | Fraud Ops Lead | Data Science Lead | Card Payments Lead | Compliance | IT Infra
Project Charter approval | A | R | C | C | C | I | I
Business requirements (BRD) sign-off | I | A | R | C | C | C | I
Functional requirements (FRD) sign-off | I | A | C | R | R | C | C
Data pipeline & feature store build | I | A | I | R | I | I | C
Model development & training | I | A | C | R | I | C | I
Scoring API & switch integration | I | A | I | C | R | I | R
Model risk validation | I | C | I | C | I | R | A
Champion/challenger pilot execution | I | A | R | R | C | I | I
Go / no-go decision for production cutover | A | R | C | C | C | C | I
Production cutover & go-live | I | A | C | C | R | I | R
Post-implementation review | A | R | C | C | C | I | I
Ongoing model monitoring & retraining | I | C | I | R | I | I | I
Steering Committee reporting | A | R | I | I | I | I | I
Notes
• Each activity has exactly one Accountable (A) party; multiple parties may be Responsible (R).
• The Project Delivery Manager (Mautik Patel) holds cross-cutting accountability for schedule, budget, and scope, and is Accountable for the majority of delivery-phase activities.
• Compliance holds sole Accountability for model risk validation given regulatory ownership under the Bank's Model Risk Management policy.
• The CRO (Sponsor) is Accountable for the initial charter and the final go/no-go and steering committee reporting lines, reflecting executive risk ownership.