## Slide 1
PURNIMA BANK
SentinelAI Fraud Detection Platform
Stakeholder Register
& Communication Plan
Stakeholder Analysis, Engagement & Communication Cadence
DOCUMENT OWNER Mautik Patel, Project Delivery Manager
VERSION 1.0 DATE January 22, 2026
VERIDIAN BANK · SentinelAI Fraud Detection Platform
Confidential – Internal Use Only

## Slide 2
SECTION 1
Stakeholder Register
Power / interest mapping and engagement strategy for each key stakeholder group.
Stakeholder | Role | Power | Interest | Engagement Strategy
Sarah Whitfield | CRO / Sponsor | High | High | Manage closely – monthly steering committee, immediate escalation of high risks
David Okonjo | Head of Fraud Ops | High | High | Manage closely – bi-weekly workstream syncs, direct input on case workflow design
Priya Nataraj | Head of Data Science | High | High | Manage closely – sprint reviews, joint model validation planning
Marcus Webb | Head of Card Payments | High | Medium | Keep satisfied – monthly integration checkpoint, early POC involvement
Compliance / Legal | Model Risk & Regulatory | High | Medium | Keep satisfied – engaged from Phase 2 to avoid late-stage rework
Fraud Analysts (front line) | End Users | Low | High | Keep informed – UAT participation, training sessions pre-go-live
Customer Experience Team | Downstream Impact | Low | Medium | Keep informed – quarterly updates on false-decline improvement metrics
Enterprise IT Infrastructure | Platform Support | Medium | Low | Monitor – involved at integration and cutover phases
VERIDIAN BANK · SentinelAI Fraud Detection Platform
Confidential – Internal Use Only

## Slide 3
SECTION 2
Communication Plan
Cadence, channel, and ownership for recurring project communications.
Communication | Audience | Frequency | Channel | Owner
Steering Committee update | Sponsor, PMO, workstream leads | Monthly | In-person / Teams + deck | Mautik P.
Core team stand-up | Delivery team | Weekly | Teams call | Mautik P.
Sprint review & demo | Data Science, Engineering, Fraud Ops | Bi-weekly | Teams call | Priya N.
Status report | Sponsor, Steering Committee | Weekly | Email (report template) | Mautik P.
Risk & issue review | Core team, Compliance | Weekly | Teams call / RAID log | Mautik P.
Analyst training & UAT briefing | Fraud Ops analysts | Twice (pre-pilot, pre-go-live) | In-person workshop | David O.
Executive go-live readiness review | CRO, all workstream leads | Once, prior to cutover | In-person | Mautik P.
Post-implementation review | Sponsor, Steering Committee | Once, 90 days post go-live | Report + presentation | Mautik P.
VERIDIAN BANK · SentinelAI Fraud Detection Platform
Confidential – Internal Use Only

## Slide 4
SECTION 3
Escalation Path
Four escalation levels ensure issues reach the right decision-maker within a defined time target.
1
LEVEL 1
Core Team Issue
Resolved within workstream, logged in RAID log.
Target: 48 hours
2
LEVEL 2
Cross-Workstream Conflict
Medium/high risk escalated to Project Delivery Manager.
Target: 3 business days
3
LEVEL 3
Budget, Scope or Timeline Impact
Escalated to Steering Committee at next review, or emergency session if severe.
Target: Next review / emergency session
4
LEVEL 4
Regulatory or Reputational Risk
Immediate escalation to CRO and Compliance regardless of scheduled cadence.
Target: Immediate
VERIDIAN BANK · SentinelAI Fraud Detection Platform
Confidential – Internal Use Only